Micro-Acquisition process 1: pre-contracting process (this process assumes client is in IITB)
Client
Admin – IT Strategy team
CFOB – procurement innovation team
IITB – FPS team
Send email to MA team expressing interest
Create repo where work will be delivered (if required)
Complete the PIF (use the MA PIF template)
Get section 32 sign off on the PIF
Send the signed PIF and the opportunity statement to FPS
Translate the opportunity text
Finalize the opportunity statement
Meeting to understand need/start documenting opportunity
(use opportunity template)
Post the opportunity on the website (refer to the publishing checklist and comms plan)
Document opportunity in the tracker
Create the web page for the opportunity
Set up a meeting with the client
Add details to the tracker
Yes
Go
(yes or no)?
Approved (yes or no)?
No
Reserve the funds (in SAP)

---
Micro-Acquisition process 2A: solicitation process (question from supplier)
Supplier
Write answer
Translate question and answer
Question about an open opportunity
Send a tweet and a notification message to mailing list (and anyone who has applied already)
Respond to the supplier
Post Q&A on the opportunity page
Respond to supplier to advise the answer has been posted
Update the Q&A section of the website if this is a common question
Inbox triage
Question about MA in general
Supplier sends email asking a question

---
Micro-Acquisition process 2B: Solicitation process
Send an email connecting the supplier with the client
Complete the evaluation and send results to MA mailbox
Update opportunity status to closed
Send evaluation package to client (see the admin guide)
Select the supplier (random number) & document decision
Notify the winning supplier via email.
Notify the other applicants via Notify message
Save the signed T&C document on the SharePoint site
Consolidate and anonymize applications (see the admin guide)
Evaluation
ok?
Sign one page terms and conditions
Supplier sends in application form

---
Micro-Acquisition process 3: contract administration
The code is merged into the delivery repository and the Open Resource Exchange is updated with a link to the code
Answer questions
Assess the code against the acceptance criteria
Supplier is advised that the code has been accepted
Code meets the criteria?
Provide support if required
Provide support if required
Provide support if required
Provide support if required
Provide support if required
Deliver finished code
Adjust the code (see exception process for cancellation due to non-delivery)
Start work on either the delivery repo or repo of their choice
Questions?

---
Micro-Acquisition process 4: post-contractual process (assumes client is from IITB)
IITB – FPS team
Section 34 manager signs documents
Save the countersigned T&C document on Sharepoint
Send entrusted email for section 34 signature
Enter approved invoice into SAP
Card doc created in SAP
Terms and Conditions document countersigned by the person in FPS issuing payment
Issue payment
Supplier receives payment
Send invoice

---
Micro-Acquisition Exception Process: Process 1 pre-contracting process (non-IITB client)
IITB – FPS team
Complete the opportunity statement
Initiate budget transfer for opportunity fixed price amount
Translate the opportunity text
Send email to MA team expressing interest
Budget transferred or agreement from IITB to risk manage until transfer complete
Create repo where work will be delivered (if required)
Meeting to understand need/start documenting opportunity
(use opportunity template)
Post the opportunity on the website (refer to the publishing checklist and comms plan)
Document opportunity in the tracker
Get section 32 sign off on the PIF
Notify the client that funds have been reserved
Create the web page for the opportunity
Complete the PIF (use the MA PIF template)
Send the signed PIF and the opportunity statement to FPS
Set up a meeting with the client
Document opportunity in the tracker
Go
(yes or no)?
Approved (yes or no)?
Reserve the funds (in SAP)

---
Micro-Acquisition Exception Process: Process 4 - post-contractual process (non-IITB client)
IITB – FPS team
Section 34 manager signs documents
Save the countersigned T&C document on Sharepoint
Send entrusted email for section 34 signature
Enter approved invoice into SAP
Card doc created in SAP
Terms and Conditions document countersigned by the person in FPS issuing payment
Issue payment
Supplier receives payment
Send invoice

---
Micro-Acquisition Exception process – non-delivery
Client advises MA team of that supplier has not delivered on deadline
Confirm a new delivery date with the supplier
Send an email to the supplier asking if they would like an extension or if they would like to discontinue
Send an email to the supplier with the text from the agreement confirming termination of contract with no payment
End of process, move to Process 4 (post-contractual)
Supplier delivers code
Supplier advises MA team of inability to deliver
Supplier wants to continue

---
Micro-Acquisition Exception process – dispute resolution process
CFOB – procurement innovation
Resolve dispute (with supplier)
Send final dispute response to Supplier and MA mailbox
Dispute resolved
Inbox triage/forward dispute to client
Provide support if required
Document the dispute and the resolution on SharePoint
Provide support if required
Send dispute concerns to MA mailbox